CS-M74

SOFTWARE PRODUCT DEVELOPMENT

Attempt 2 questions out of 3

Question 1

(a)	Contrast and compare the waterfall model (or 'classical' model) of software development and the iterative/incremental approach.

[10 marks]

(b)	Briefly describe another approach to software development, indicating its benefits and the type of application area to which it is best suited.

[5 marks]

(c)	(i)	Explain and contrast white box testing and black box testing.

[4 marks]

(ii)	What type of program errors can be detected using static analysis?

[2 marks]

(d)	What is the Capability Maturity Model and what purpose does it serve?

[4 marks]

Question 2

(a)	Briefly describe the protection provided to intellectual property via copyright, patents and trademarks.

[9 marks]

(b)	Explain the term "Copyleft" and discuss what is meant by "Free Software" (as used by Richard Stallman and the Free Software Foundation).

[5 marks]

(c)	Recently there have been moves to introduce changes to the legislation in Europe to allow patent protection for computer programs. What are the main arguments for and against such a change?

[4 marks]

(d)	Consider the following two requests from a lecturer in the Computer Science department of a university to the university library:

(i) Can I have a report of the number and length of borrowings of each of the recommended texts for the module I teach?

(ii) Can I have a report detailing for each student taking the module that I teach, a list of the books borrowed by them and dates of each borrowing?

Discuss the legal and ethical issues that arise from these requests.

[7 marks]

Question 3

(a)	(i)	In the context of project management, explain the following terms: task, milestone,

critical path, and slack.

[6 marks]

(ii)	For each of the tasks listed below, determine the earliest and latest event time, the

slack, and whether or not the task is on the critical path. Draw a network chart and

highlight the critical path.

Task	Predecessor	Duration

A	None	1

B	None	3

C	A	3

D	B, C	5

E	C	1

F	D	4

G	E, F	3

H	G	2

I	G	2

J	H, I	5

K	J	6

[8 marks]

(b)	What is a Gantt chart? How is it used to support the project management task? How does its use differ from that of the network chart?

[5 marks]

(c)	Professional organisations for software developers such as the British Computer Society (BCS) and the Association for Computing Machinery (ACM) have developed a Code of Conduct for their members. What do such Codes contain and what purpose do they serve?

[6 marks]